## UI
NO | Issue Description | Status | Owner | Start Date | End Date | Comments | Testing
1 | When files are >1000(N), webserver is not responding | In Progress | Chakrapani | 1st Mar |  | Batch wise | Failed
2 | Not able to upload .jpeg | Fixed | Chakrapani | 28th Feb |  |  | Pass | Pass
3 | Delete the .p file when images are changed | In Progress | Jadeja | 1st Mar |  |  | Check | failed
4 | Number of photos retrieved in the result section is limited 10, make it editable from GUI | Fixed | Jadeja | 1st Mar |  |  | Pass | failed
5 | The view/direction of photos displayed are not uniform | Fixed | Jadeja | 1st Mar |  |  | Pass | failed
6 | Images uploaded by photographer should be compressed and stored | OnHold | Chakrapani
7 | Move the server to the professional account | In Progress | Jadeja | 2020-03-28 | 2020-03-28
8 | DAR on AWS, Google and Microsoft subscription | In Progress | Jadeja | 2020-03-27 | 2020-03-27
9 | Download all button | Fixed | Chakrapani | 2nd Mar | 2nd Mar |  | Pass | failed
10 | Display the images in tumbnails | Fixed | Chakrapani |  |  |  | Pass
11 | Multiple person uploading - user Registration | In Progress | Jadeja | 2020-03-24 | 2020-03-24
| Publish development/production environment | In Progress | shiva
12 | When the directory/date folder entered is not available, there is no pop up/error saying "no such directory exists" *Only list folder which are there in server | In Progress | Chakrapani | 2020-03-23 | 2020-03-23 | Need to Start |  | failed
13 | Delete the user data once the Athlete logs out | In Progress | Chakrapani | - | - | Already Implemented -Done
14 | * Change the name to "Houndog by TeamFotog" * Change name from ImageProcessing to FaceDetection application. * Copy reserved company name(San Research, Sanresearch69@gmail.com) | In Progress | Chakrapani | 2020-03-23 | 2020-03-23 | Need to Start
15 | Progress bar for data uploading | In Progress | Chakrapani | 2020-03-25 | 2020-03-27 | Need to Start
16 | Change backgroud to faceDetection, PhotoGrapher and Athelte pages | In Progress | Chakrapani | 2020-03-27 | 2020-03-27 | Need to Start
17 | Login/Logout Features
18 | If Two users trying to upload same date and same stadium, we are using same folder for different uploads[different sessions]
19 | Binding Searched results one by one not at a time with the progressbar asynchronosly
20 | Drag and Drop feature for uploading
21 | Selection of sport while uploading, if not known then specify under other category
22 | Searched Results UI Change